## Gantt Tasks
ID | Task | Owner | Start | Finish | Duration (days) | Predecessors
1 | Project kickoff and scope alignment | Member 1 | 2026-02-25 | 2026-02-27 | 3
2 | Requirements finalization and workflow mapping | Member 2 | 2026-02-26 | 2026-03-01 | 4 | 1
3 | Data model and API contract drafting | Member 1 | 2026-03-02 | 2026-03-05 | 4 | 2
4 | Frontend screen flow planning and UI baseline | Member 2 | 2026-03-03 | 2026-03-06 | 4 | 2
5 | Core product/baki/customer CRUD + list workflows | Member 1 | 2026-03-25 | 2026-03-26 | 2 | 3,4
6 | Stock expiry, low-stock alerts, movement, reorder suggestions | Member 1 | 2026-03-25 | 2026-03-26 | 2 | 5
7 | PR integration milestone #1 and #2 | Member 2 | 2026-03-25 | 2026-03-26 | 2 | 5
8 | Dashboard utility and hybrid session verification integration | Member 2 | 2026-03-26 | 2026-03-27 | 2 | 7
9 | Baki/customer analytics, repayment flow, filters, trust indicators | Member 1 | 2026-03-26 | 2026-03-27 | 2 | 5
10 | Architecture lock and SQLite-Mongo synchronization | Member 1 | 2026-04-10 | 2026-04-10 | 1 | 8,9
11 | Authentication and authorization hardening | Member 1 | 2026-04-10 | 2026-04-11 | 2 | 10
12 | Architecture-lock milestone merge and QA checks | Member 2 | 2026-04-10 | 2026-04-10 | 1 | 10
13 | Trust scoring system implementation | Member 1 | 2026-04-11 | 2026-04-12 | 2 | 11
14 | Trust score monitoring (RBAC), model training and backtesting | Member 1 | 2026-04-12 | 2026-04-13 | 2 | 13
15 | Trust-score milestone merge and regression verification | Member 2 | 2026-04-12 | 2026-04-12 | 1 | 14
16 | Markov queue forecasting and expected outcomes | Member 1 | 2026-04-21 | 2026-04-22 | 2 | 14
17 | Forecasting milestone merge and validation | Member 2 | 2026-04-21 | 2026-04-22 | 2 | 16
18 | Voice recognition, assistant feedback, and customer-flow UX improvements | Member 1 | 2026-04-24 | 2026-04-25 | 2 | 16
19 | Final stabilization, integration checks, and reporting handoff | Member 2 | 2026-04-24 | 2026-04-25 | 2 | 17,18